Australia’s National
Science Agency

DRAFT v1 – for comment

July 2022

Guidelines for the development of a Governance Framework for the Australian National Soil Information System (ANSIS)

This document presents the guidelines for the development of a proposed Governance Framework for the Australian National Soil Information System (ANSIS) during the period of the ANSIS Project. This document meets an ANSIS Project milestone requirement for the Australian Government’s Department of Agriculture, Fisheries and Forestry.

Palmer, J., Wilson, P., Gregory, L., Stower, L., Kostanski, L., Lemon, D., Lee, A., Box, P. (2022) Guidelines for the development of a Governance Framework for the Australian National Soil Information System (ANSIS). CSIRO: Brisbane.

CSIRO Agriculture and Food

Important disclaimer

CSIRO advises that the information contained in this publication comprises general statements based on scientific research. The reader is advised and needs to be aware that such information may be incomplete or unable to be used in any specific situation. No reliance or actions must therefore be made on that information without seeking prior expert professional, scientific and technical advice. To the extent permitted by law, CSIRO (including its employees and consultants) excludes all liability to any person for any consequences, including but not limited to all losses, damages, costs, expenses and any other compensation, arising directly or indirectly from using this publication (in part or in whole) and any information or material contained in it.

Contents

Contents	2

Glossary	4

Executive summary	5

1	Overview of the Governance Framework: ANSIS as a socio-technical system	7

1.1	Principles that underpin the Governance Framework	7

1.2	Alignment processes and policies for ANSIS Governing Community	8

1.3	Key policy recommendations and priorities	9

2	The Governance Framework ‘Viewpoints’	11

2.1	Enterprise Viewpoint	11

2.2	Information Viewpoint	25

2.3	Computational Viewpoint	27

2.4	Engineering Viewpoint	27

2.5	Technology Viewpoint	29

3	Governance of ANSIS post Project	31

4	References	32

5	Appendix	33

Acknowledgements

ANSIS is supported by funding through the Australian Government National Soil Strategy (Department of Agriculture, Fisheries and Forestry) in collaboration with CSIRO and partner organisations.

CSIRO and the authors acknowledge the Traditional Owners of the lands and seas that we live and work on across Australia and pay their respect to Elders past and present. CSIRO and the participants recognise that Aboriginal and Torres Strait Islander peoples have made and will continue to make extraordinary contributions to all aspects of Australian life including land, culture, economy and science.

This document is based on Box, Paul; Levett, Kerry; Simons, Bruce; Wong, Megan (2019) Guidelines for the development of a Governance Framework for the Agricultural Research Federation (AgReFed) Version 1.1. CSIRO.

Glossary

| Term | Definition |
| --- | --- |
| Soil data | Data and information regarding the natural resource, soil, obtained through soil survey, assessments and relevant research by public and private sector organisations and individuals. The scope of soil data relevant to ANSIS is as defined by the ANSIS Project Committee. |
| ANSIS Data | Data made available through ANSIS, as provided by Data Providers, and standardised and harmonised via ANSIS processes that are compliant with agreements between the ANSIS Project Committee and ANSIS Partners, and/or ANSIS policies. |
| ANSIS FAIR Data | FAIR data is Findable, Accessible, Interoperable and Re-useable. ANSIS Fair Data has been assessed by the Data Provider and reviewed (by the ANSIS Data Steward) as being compliant with the ANSIS FAIR Data Policy. |
| The ANSIS Project (the Project) | The collaborative Project, led by CSIRO and funded by the Department of Agriculture, Fisheries and Forestry (2021-2023), which will develop the Australian National Soil Information System (ANSIS), the System. |
| ANSIS (the System) | The Australian National Soil Information System (ANSIS), which will provide improved access to data and information to help sustainably manage Australia’s soil. The ANSIS Project will develop ANSIS, the System, with the intention for ANSIS to become an ongoing national information infrastructure, which will continue past the life of the Project. |
| ANSIS Community | Encompasses all organisations, entities, groups, and individuals (e.g., Data Providers, soil stakeholders, soil data users) who contribute to, utilise or derive benefit from ANSIS. |
| ANSIS Governance Community | Encompasses all governing groups with members from the ANSIS Project team, funders, ANSIS Partners (e.g. Data Providers) and other invited stakeholders that undertake defined roles that enable the collaborative development and operation of ANSIS. |
| ANSIS Partners | Organisations or entities (e.g., Data Providers) that have a contractual arrangement or agreement with ANSIS. |
| ANSIS Project Committee (Project Committee) | The Project Committee members are representatives from the lead organisation (CSIRO) and the funding body (DAFF). The Project Committee is answerable to contractual obligations with the funding body. It is responsible for decision making regarding the overall strategic direction, project management and business operations, as well as technical systems implementation for the ANSIS Project. |
| ANSIS Consultative Group (Consultative Group) | Provides consultative support, advice and recommendations to the Project Committee for strategic decision making. The Consultative Group members are representatives from ANSIS Partners and other invited key stakeholders. |
| ANSIS Science and Technical Reference Group (Technical Group) | Provides consultative support, advice and recommendations for technology choices, system implementation, data standards and acceptable qualifying levels to the Project Committee for technical decision making. The Technical Group members are representatives from ANSIS Partners and other invited key stakeholders. |
| ANSIS Trusted Repository | Is a soil data information system and managed repository that has been assessed and certified as compliant with the ANSIS Trusted Repository Policy by the ANSIS Collections Steward. |
| Data governance | The planning, oversight, and control over management of data and the use of data and data-related resources (DM-BOK 2nd Edition) through human and technical systems to achieve a collectively agreed goal. This is the social component of a system that interacts with the technical and informational system viewpoints. |
| Physical sample | A sample collected of a physical object, e.g., soil sample. |
| Data Steward | A data steward is a person or organisation delegated the responsibility for managing a specific set of data resources (ISO/IEC 11179). This is undertaken to achieve collective socio-technical goals, including FAIRness and interoperability of data. |

Executive summary

This document is a product of the Australian National Soil Information System (ANSIS) Project led by CSIRO. The intent of the document is to outline guidelines for the development of a proposed Governance Framework for ANSIS, initially enacted through the ANSIS Project, hereafter referred to as “the Project”. The Project will develop ANSIS (“the System”), with the goal of providing improved access to, and use of, nationally consistent soil data and information needed to help sustainably manage Australian soil. The intention is for ANSIS to become a well-managed and ongoing national soil information infrastructure, with transition to agreed collaborative governance arrangements past the life of the Project (June 2023).

This document provides high level design and guidelines for the initial implementation of the proposed ANSIS Governance Framework, a socio-technical arrangement that:

- Provides a framework for the governance of ANSIS (the System) for the duration of the Project (2021-2023).

- Brings independent partner and key stakeholder organisations together to provide consultative support to guide strategic and technical decisions about soil data sharing through ANSIS.

- Will guide ANSIS Partners (e.g., Data Providers) and the broader ANSIS Community through a set of clearly defined roles, responsibilities, policies, and procedures.

- Articulates that collaborative governance of ANSIS after the life of the Project will be different to the proposed governance during the Project and that a transition plan will be needed.

The document is intended primarily for use by the members of the ANSIS Governance Community.

The ANSIS Governance Framework for the Project period encompasses a:

- Social architecture, including:

  - The organisational form of the ANSIS Project.

  - A Governance Community comprising:

    - the ANSIS Project Committee, hereafter referred to as the Project Committee, consisting of representatives from CSIRO (Project lead) and the Department of Agriculture, Fisheries and Forestry (DAFF) (Project funders)

    - two supporting groups: the ANSIS Consultative Group, hereafter referred to as the Consultative Group, and the ANSIS Science and Technical Reference Group, hereafter referred to as the Technical Group whose membership is made up of representatives of the ANSIS Partners and other invited key stakeholders.

  - Policies that will be produced by the Project Committee in consultation with the Consultative Group and Technical Group, to guide ANSIS Partners (e.g., Data Providers), ANSIS operations and the broader ANSIS Community.

  - Roles performed by ANSIS Governance Community members.

  - Processes to ensure long-term availability of FAIR soil data through ANSIS.

- Technical and Information architectures to improve the findability, discoverability, accessibility and reusability (FAIRness) of soil data and information through ANSIS.

This document is presented in three main parts:

- An overview of the guidelines for the development of a proposed Governance Framework for ANSIS during the Project.

- The Social, Technical and Information architectures to improve the findability, discoverability, accessibility and reusability (FAIRness of) soil data through ANSIS.

- A suggested process to develop a future collaborative governance model for ANSIS past the life of the Project.

To finalise the ANSIS Governance Framework for the Australian National Soil Information System (ANSIS) for the Project duration, the following needs to occur:

- Approval of this Draft ANSIS Governance Framework document by the Department of Agriculture, Fisheries and Forestry (DAFF).

- Draft Terms of Reference for the Project Committee, the Consultative Group and the Technical Group to be developed by ANSIS Governance team and reviewed by the ANSIS Governance Community and approved by DAFF.

- Establishment of the Consultative Group and Technical Group by the ANSIS Project Committee through ANSIS Partners and invited key stakeholders nominating representatives to sit on these bodies.

# Overview of the Governance Framework: ANSIS as a socio-technical system

## Principles that underpin the Governance Framework

This document is a product of the Australian National Soil Information System (ANSIS) Project led by CSIRO. The intent of the document is to outline guidelines for the development of a proposed Governance Framework for ANSIS, initially enacted through the ANSIS Project, hereafter referred to as “the Project”. The Project will develop ANSIS (“the System”), with the goal of providing improved access to, and use of, nationally consistent soil data and information needed to help sustainably manage Australian soil. The intention is for ANSIS to become a well-managed and ongoing national soil information infrastructure, with transition to agreed collaborative governance arrangements past the life of the Project (June 2023).

This document provides high level design and guidelines for the initial implementation of the proposed ANSIS Governance Framework, a socio-technical arrangement that:

- Provides a framework for the governance of ANSIS (the System) for the duration of the Project (2021-2023).

- Brings independent partner and key stakeholder organisations together to provide consultative support to guide strategic and technical decisions about soil data sharing through ANSIS.

- Will guide ANSIS Partners (e.g., Data Providers) and the broader ANSIS Community through a set of clearly defined roles, responsibilities, policies, and procedures.

- Articulates that collaborative governance of ANSIS after the life of the Project will be different to the proposed governance during the Project and that a transition plan will be needed.

The Governance Framework is described using the Reference Model for Open Distributed Processing (RM-ODP), though mainly focusses on the first of the five architectural ‘Viewpoints’ for specifying distributed information systems which include:

- The Enterprise Viewpoint - purpose, scope and policies of a system, and socio-economic and institutional environment within which it operates (the social architecture).

- The Information Viewpoint - scope and nature of the data content within ANSIS (the information architecture).

- Three Technical Viewpoints - the Computational, Engineering and Technology Viewpoint configuration of the system (the technical architecture).

The ‘social architecture’ is based around the following key concepts:

- The Project lead agency, answerable to contractual obligations, developing ANSIS (the System) for the duration of the Project.

- Independent and autonomous Data Provider communities, which may become ANSIS Partners, and the collective ANSIS Governance community within which they participate.

- The roles performed by the ANSIS governing bodies (e.g., Project Committee, Consultative Group and Technical Group) to provide consultative support and decisions to govern ANSIS and contribute to the technical development aspects of the System.

- The policies and agreements that are produced through governance mechanisms (decision making bodies and process) that guide collective and individual actions.

- Two processes to align individual Data Providers’ data and repositories with agreed collective direction. These alignment processes are adapted from  FAIR Guiding Principles for scientific data management and stewardship (FAIR) and CoreTrustSeal Data Repositories Requirement (CoreTrustSeal).

## Alignment processes and policies for ANSIS Governing Community

From ‘my data’ to Our FAIR data.

- Individual providers’ heterogeneous data and provisioning arrangements can be brought into alignment with agreed ANSIS levels of FAIRness and repository trustedness (Figure 1).

- ANSIS uses the FAIR Data Policy and ANSIS Trusted Repository Policy as non-binding, guiding principles to define the qualifying levels required for data to be provided as ANSIS Data.

Figure 1: Diagram of ANSIS data alignment processes and policies.

## Key policy recommendations and priorities

### Governing policies

Partnership Policy and Contracts

- Define and formalise the responsibility of ANSIS Partners (e.g., Data Provider Communities).

- Define and endorse the protocols for joining and exiting ANSIS.

- Establish contracts with ANSIS Partners (e.g., Data Provider Communities).

Strategic and Business Policies

- High level business decisions such as areas of focus, strategy and engagement that guide future direction of ANSIS.

Role Assignment Policies

- Refine, develop Terms of Reference for the governing bodies and formalise the initial recommended roles that have been defined in this document.

- Define and formalise a process by which roles can be established and may be changed (and by whom) over time, for example the addition of new roles or the change in responsibilities or accountabilities for an existing role.

### Technical policies

ANSIS FAIR Data Policy

- Adoption and promulgation of the ANSIS FAIR Data Policy, together with proposed initial ANSIS FAIR Data qualifying thresholds.

- Determine permissible licensing and access arrangements for ANSIS data in line with Data Provider requirements and constraints, if any.

- Agree on initial data standards, information model and ANSIS data delivery approaches and tools.

ANSIS Trusted Repository Policy

- Further define and adopt the ANSIS Trusted Repository Policy described in this document, together with proposed initial qualifying levels.

Priority governance actions for ANSIS

- Approval of this Draft ANSIS Governance Framework document by the Department of Agriculture, Fisheries and Forestry (DAFF).

- Draft Terms of Reference for the Project Committee, the Consultative Group and the Technical Group to be developed by the ANSIS Project Committee and reviewed by the ANSIS Governance Community and approved by DAFF.

- Establishment of the Consultative Group and Technical Group by the ANSIS Project Committee through ANSIS Partners (e.g., Data Providers) and invited key stakeholders nominating representatives to sit on these bodies.

# The Governance Framework ‘Viewpoints’

The Guidelines for the Governance Framework is described using the Reference Model for Open Distributed Processing (RM-ODP), though mainly focusses on the first of the five architectural ‘Viewpoints’ for specifying distributed information systems which include:

- The Enterprise Viewpoint - purpose, scope and policies of a system, and socio- economic and institutional environment within which it operates (the social architecture).

- The Information Viewpoint - scope and nature of the data content within ANSIS (the information architecture).

- Three Technical Viewpoints - the Computational, Engineering and Technology Viewpoint configuration of the system (the technical architecture).

These Viewpoints are described in the next section of this document. The Enterprise Viewpoint is the focus of the document and has been articulated in detail, while the Information and Technical viewpoints are presented in high level summary form.

## Enterprise Viewpoint

The Enterprise Viewpoint focuses on the purpose, scope and policies of a system and the socio-economic and institutional environment within which it operates.

The Enterprise Viewpoint describes the social architecture of the Australian National Soil Information System (ANSIS).

The Enterprise Viewpoint presents

- An approach to defining the Governance Framework.

- The decision-making mechanisms through which decisions can be made.

- The polices, roles and processes through which the community collaborates to achieve FAIR soil data.

### Key framework concepts

The Enterprise Viewpoint defines relevant aspects of the organisational, business and social context within which ANSIS exists for the duration of the Project (2021-2023). It aims to define the purpose of the System, its partners and stakeholders, how they interact with the system, and their requirements.

Since the main goal of the ANSIS Project is to establish an infrastructure that efficiently delivers more accessible, useable and nationally consistent soil data to users than current processes, this document focusses on the Provider Community (rather than the end user community) and how they participate in and make decision about ANSIS and its operation.

A community defines a set of participants and how they behave to achieve shared objectives. The behaviour of the community is shaped and guided by the definition of policies (e.g. related to data standards or decision-making) that define how different roles interact within and between communities.

The collaboration agreement between ANSIS and ANSIS Partners (e.g., Data Provider Communities) may be defined by a contract, to which both parties are bound.

The relevant behaviours of the community can be described as a series of processes that conform to agreed policies (or rules).

For ANSIS, two key alignment processes are used to align existing practices and approaches of individual Data Providers to agreed ANSIS approaches. The two principle alignment processes are the ANSIS FAIR Data Policy based on FAIR principles and including qualifying thresholds, and ANSIS Trusted Repository requirements, based on CoreTrustSeal requirements (see Appendix 3 for more information).

Policies set by the Governance Community determine acceptable minimum levels of FAIRness of data and trustworthiness of repositories that providers need to meet in order to share data through ANSIS.

Community - is a collection of participants (human and other entities) that interact to achieve shared objectives.

Policy - agreements that are produced by, and guide and shape the behaviour of the community.

Contracts - binding agreements between parties (e.g., ANSIS Project lead agency and ANSIS Partners) that outline the how both parties will collaborate to achieve the ANSIS objectives.

Roles - the roles that enable ANSIS, the System, to function. They comprise governance and management roles, and the substantive stewardship roles that enable delivery of FAIR soil data.

Processes - are the interactions between roles, shaped by policies that enable the achievement of community objectives.

### ANSIS - A proposed socio-technical system

ANSIS encompasses Data Provider communities, social components such as roles, policies and alignment processes and technical components for enabling the access and use of soil data (Figure 2).

Figure 2: Diagram of a proposed socio-technical system for ANSIS.

### The ANSIS Community

A number of discrete organisations or bodies are involved in development and operation of ANSIS (Figure 3) during the Project phase. These are defined as communities.

- ANSIS Governance Community – this is the community composed of all the various communities and groups that provide input to the governance of ANSIS and enable the System to operate. This community encompasses:

  - The Project Committee, with representatives from the lead organisation (CSIRO) and the funding body (DAFF).

  - The Consultative Group, with representatives from ANSIS Partners (e.g., Data Provider Communities) and invited key stakeholders.

  - The Technical Group, with representatives from ANSIS Partners (e.g., Data Provider Communities) and invited key stakeholders.

  - Other substantive roles, for example the ANSIS Data Steward and the ANSIS Standards and Vocabularies Steward.

- ANSIS Partners – individuals and organisations (e.g., Data Providers) that have a contractual arrangement or agreement with the ANSIS lead organisation.

- Stakeholder Communities – broader communities with an interest in ANSIS.

- The Domain Authority Communities – the organisations responsible for developing, publishing and governing vocabularies, information models and other kinds of standards. These may be pre-existing external communities that govern standards that are relevant for ANSIS. In the soils domain this may include, for example, the national Committee on Soil and Terrain, the Australian Soil and Plant Analysis Council, the Australian Soil Science Society etc.

- ANSIS Funding Body/Bodies – communities that provide funding for ANSIS.

- User Community (who are not discussed further in this governance framework document, but who are intrinsically important to the design, delivery and operation of ANSIS to ensure it meets user needs and expectations).

The ANSIS Community encompasses all organisations, entities, groups, and individuals (e.g., Data Providers, stakeholders, soil data users) who contribute to, utilise or derive benefit from ANSIS.

Figure 3: Diagram of the ANSIS Community and associated communities.

#### ANSIS Community – Project lead agency and funding body

While ANSIS is under development during the Project phase (2021-2023), it is proposed that the Project Committee coordinate the management of the Project. The Project Committee members are representatives from the lead organisation (CSIRO) and the funding body (DAFF). The Project Committee is answerable to contractual obligations with the funding body. It is proposed that it be responsible for decision making regarding the overall strategic direction, project management and business operations, as well as technical systems development, implementation and operation for the ANSIS Project. Decisions will be supported by advise and recommendations from ANSIS Partners and other key stakeholders, through the Consultative Group and Technical Group.

#### ANSIS Community – ANSIS Partners (e.g., Data Provider Communities)

ANSIS Partner participation and relationships in ANSIS are defined using Communities and Roles (Figure 4).

ANSIS Partners (e.g., Data Provider Communities)

- Organisations or entities that have a contractual arrangement or agreement with the ANSIS lead organisation.

- ANSIS Partners are represented by their own autonomous community (comprising a Terms of Reference) and systems.

- Each individual community is autonomous, making decisions about how it organises itself.

Participation in ANSIS

- ANSIS Partners are given a voice to provide advice and recommendations about decisions that affect them and the community to which they are contributing.

- Partner involvement is central to building and sustaining a collaboratively governed ANSIS.

Figure 4: Diagram of an ANSIS Partner (using a Data Provider community as an example) and their proposed participatory roles and interactions in the ANSIS Governance Community.

What you need to know and do as an ANSIS Partner in data provision

To participate in ANSIS as an ANSIS Partner Data Provider you will be expected to:

- Establish a contract/agreement with the ANSIS lead organisation and/or abide by the ANSIS policies and terms of reference.

- Nominate one or more people to act as representative(s) of your Data Provider Community in the Consultative Group and the Technical Group.

- Identify a Provider Collection Custodian - a person to represent the interests of and act as point for contact for the data collection(s) that you contribute to ANSIS.

#### ANSIS Community – Substantive Roles

Two other significant roles are proposed for the ANSIS Governance Community:

- ANSIS Data Steward

- Reviews and validates ANSIS FAIR Data Self-assessments.

- Reviews and validates the ANSIS Trusted Repository Self-assessment.

The ANSIS Data Steward will work with Data Provider Communities to assist them in complying with agreed policies.

- ANSIS Standards and Vocabularies Steward

- Coordinates and administers standards development and governance.

The ANSIS Data Steward and ANSIS Standards and Vocabularies Steward could be filled by a member of the lead agency, a Provider Community, or a third party tasked with the role. A single person may perform multiple roles.

#### ANSIS Community – Domain Authority Communities

Domain Authority Communities are the organisations responsible for developing, publishing and governing vocabularies, information models and other kinds of standards. These may be pre-existing external communities that govern standards that are relevant for ANSIS. In the soils domain this may include, for example, the National Committee on Soil and Terrain, the Australian Soil and Plant Analysis Council, the Australian Soil Science Society etc.

ANSIS Community – Stakeholders

Stakeholders are communities with an interest in ANSIS.

#### ANSIS Community – Users

ANSIS aims to provide accessible and useful data for users. Users are not considered further in this governance document.  Important input from users regarding the design and operation of ANSIS will be achieved through stakeholder engagements, user reference panels and ANSIS use case activities.

### The ANSIS Governing Community – objectives, roles, and accountabilities

It is proposed that the ANSIS Governing Community will be responsible for two objectives:

Objective 1: Governing - establishing, maintaining (and terminating) the Project. This encompasses governance, coordination, management, and funding of the Project to enable it to realise objective 2.

It is proposed that the Project be governed through three related bodies (Figure 5):

- The Project Committee – responsible for the overall direction, including strategic management and (business) operations, and technical development, implementation and operational decision making for ANSIS. The Project Committee is answerable to contractual obligations with the funding body.

- The Consultative Group – provides consultative support, advice and recommendations to the Project Committee for strategic decision making.

- The Technical Group – provides consultative support, advice and recommendations for technology choices, data standards and acceptable qualifying levels to the Project Committee for technical decision making.

It is proposed that each ANSIS Partner and invited key stakeholder nominate representatives to act as members of the Consultative Group and Technical Group. The Project Committee will facilitate this process and be responsible for chairing of these Groups.

Figure 5: Governing bodies for the Project.

Objective 2: Technical operational aspects regarding achieving ANSIS objectives – defining the interactions between parties that are necessary to achieve its objectives; that is the policies, contracts, roles, responsibilities and processes of the ‘moving parts’ of the system that ensure FAIR soil data can be discovered, accessed (from ANSIS Trusted Repositories), and used by end users of ANSIS.

### The ANSIS Governance Community – governing roles and accountabilities

Table 1: Objective 1 – Proposed function and characteristics of authority structures during the Project.

|  | Project Committee | Consultative Group | Technical Group |
| --- | --- | --- | --- |
| Representation | Representatives from the lead organisation (CSIRO) and the funding body (DAFF). | Representatives of the Project Committee and each ANSIS Partner (e.g., Data Provider) and invited key stakeholders. Each ANSIS Partner or key stakeholder nominates one representative to the Consultative Group. These roles may be specified as per contractual agreements and/or through Terms of Reference. | Representatives of the Project Committee and each ANSIS Partner (e.g., Data Provider) and invited key stakeholders. Each ANSIS Partner or key stakeholder nominates one representative to the Technical Group. These roles may be specified as per the contractual agreements and/or through Terms of Reference. |
| Source of authority /Mandate | Authority to make decisions, in consultation with the ANSIS Governance Community, in accordance with its contract with DAFF and its Terms of Reference. | Provide expert knowledge that informs the Project Committee on strategic aspects. These roles may or may not be funded through the ANSIS Project. | Provide expert knowledge that informs the Project Committee of technical aspects. These roles may or may not be funded through ANSIS. |
| Main functions | - Establishment, and decisions about the overall direction and operation of ANSIS. - Establishment and oversight of the consultative and technical level authority and advisory bodies (e.g., the Consultative Group and Technical Group). - Oversight of the development and operations of ANSIS. - Represent ANSIS and communicate the benefits of ANSIS. - Engage with external domain authorities. - Delivery of the Project in accordance with contractual obligations. | - Provide consultative support, advice and recommendations to guide the overall strategic direction, governance and operation of ANSIS. - Advocate for ANSIS and communicate the benefits of ANSIS. - Engage with external domain authorities. | - Provide consultative support, advice and recommendations about technical aspects for the development and operation of ANSIS. - Advocate for ANSIS and communicate the benefits of ANSIS. - Oversight of the data and systems alignment processes. |
| Decision and recommendation areas | Enterprise Viewpoint – make decisions and policies about: - The purpose and objectives of ANSIS. - The strategic direction and (business) operation of ANSIS. - Collective business processes that the ANSIS community will use. - Deployment and maintenance procedures for ANSIS - testing deployment, implementation plans as well as the governance apparatus. - Establishment of ANSIS roles. - Exit strategy articulating approaches to exiting and terminating the ANSIS. Information Viewpoint – make decisions about: - Quality assurance practices and processes. - The publication of data through ANSIS. - Determining acceptable levels of FAIRness for publication. - Determining acceptable levels of ANSIS Trusted Repository requirements. - Identifying common information models (data structures) for ANSIS. - Deciding on semantics - provider specific and agreed community vocabularies and ontologies. Computational Viewpoint – make decisions about: - The design and deployment of common infrastructure elements such as resource discovery mechanisms. - The computational interfaces relevant for ANSIS. - The supported end-user experience (portal, data services tools and applications). Engineering and Technology Viewpoints – make decisions about: - Where the system components are deployed using what technology. | Enterprise Viewpoint – provide options and recommendations about: - The purpose and objectives of ANSIS. - Collective business processes that the ANSIS community will use. - Deployment and maintenance procedures for ANSIS - testing deployment, implementation plans as well as the governance apparatus. - Establishment of ANSIS roles. Information Viewpoint – provide options and recommendations about: - Determining what constitutes acceptable data for sharing through ANSIS (high-level). | Information Viewpoint – provide options and recommendations about: - Quality assurance practices and processes. - The publication of data through the ANSIS. - Acceptable levels of FAIRness for publication. - Acceptable levels of ANSIS Trusted Repository requirements. - Identifying common information models (data structures) for ANSIS. - Recommending semantics - provider specific and agreed community vocabularies and ontologies. Computational Viewpoint – provide options and recommendations about: - The design and deployment of common infrastructure elements such as resource discovery mechanisms. - The computational interfaces relevant for ANSIS. - The supported end-user experience (portal, data services tools and applications). Engineering and Technology Viewpoints – provide options and recommendations about: - Where the components are deployed using what technology. |
| Decision rights | Authority to make all decisions for strategic and technical aspects including those specified above for the duration of the Project. | Provide consultative support and recommendations about strategic aspects. | Provide consultative support and recommendations about technical aspects. |
| Decision making processes | Negotiated decision making between lead agency (CSIRO and funding agency (DAFF) (with DAFF decision if no consensus is reached under term of the ANSIS Project contract). | One seat/voice Options and recommendations presented to the Project Committee for decision. | One seat/voice Options and recommendations presented to the Project Committee for decision. |

### The ANSIS Governing Community – technical roles and accountabilities

Objective 2: Technical development, implementation and operation of ANSIS, the System.

It is proposed that three key substantive roles be established.

Data Provider Collection Custodian

The Provider Collection Custodian role is filled by a nominated Provider Community representative to represent the interests of the data collection in ANSIS and has responsibility for ensuring the collection’s sustained FAIRness according to agreed contracts and policies. This role may be specified as per the contractual agreements and/or through Terms of Reference. This role may or may not be funded through ANSIS.

Specific accountabilities include:

- Ensuring that the ANSIS Contract is honoured i.e. data remains FAIR according to agreed ANSIS FAIR Data Policy.

- The creation and maintenance of accurate collection metadata.

- Ensure that the metadata record is harvestable by Research Data Australia (RDA).

- Ensure data is aligned with published vocabularies endorsed by ANSIS.

- Liaise with the Provider Community roles to ensure data collections updates are consistent with ANSIS policies (e.g. around metadata quality).

- Liaise with the repository manager to ensure sustained access.

This ANSIS Community role maps most closely to the Provider Community collection manager role(s).

A Provider Collection Custodian may be responsible for more than one collection and a collection must have at least one Custodian.

ANSIS Data Steward

An ANSIS Data Steward is responsible for administering the policies and alignment processes that are set by governing bodies of ANSIS by working with Data Provider Communities to assist them in complying with agreed policies.

Responsibilities include:

- Approving data sets for publication based on governance guidelines.

- Liaising with and providing support to Data Provider Communities to complete their ANSIS FAIR Data and Trusted Repository Self-assessments.

- Providing advice, guidance and technical support to Data Provider Communities

- Validating collection metadata.

- Validating ANSIS FAIR Data Self-assessments.

- Validating ANSIS Trusted Repository Self-assessments.

ANSIS Standards and Vocabularies Steward

•	Coordinating standards and vocabulary development and updating/maintenance.

•	Validating published vocabularies.

•	Coordinating standards and vocabulary governance.

### ANSIS Partners (e.g., Data Providers) – function and roles

Each ANSIS Partner is represented as its own community (for example a 2nd tier state agency, or a 3rd tier agricultural industry or natural resource management group). Each community is autonomous and makes its own decisions about how it organises itself.

ANSIS Partners may or may not be represented in ANSIS through contractual agreements with the lead organisation or funding agency. Some ANSIS Partners my participate in a voluntary way because of recognised benefits achievable through data sharing and improved access and use.

It is proposed that ANSIS Partners nominate representatives for the Consultative Group and Technical Group and the Provider Collection Custodian role. Initially this will be constrained to active ANSIS Partner organisations directly contracted through the ANSIS Project.  A process will be developed for the addition of other voluntary ANSIS Partners and invited key stakeholders through Consultative group recommendation.

ANSIS Partners that are Data Providers comprise those engaged in operating their data repository, establishing data services and curation, management and provisioning of data (including metadata) to ANSIS.

#### Data Providers - Possible Community roles

A number of Provider Community roles necessary for the provision of FAIR data are suggested, and are mapped to Collection-Party relations from the RIF-CS schema (as used by Research Data Australia), to assist the representation of these roles in collection metadata records.

| Provider Community roles | Collection-Party relation (RIF-CS) | Description |
| --- | --- | --- |
| Provider Collection Creator | hasCollector | has been collected, generated, created or aggregated by the related party |
| Provider Collection Manager/Custodian | isManagedBy | is maintained and made accessible by the related party (includes custodian role) |
| Provider Collection Owner | isOwnedBy | legally belongs to the related party |
| Provider Collection Enhancer | isEnrichedBy | additional value provided to a collection by a party (i.e. formatting or describing to enable sharing and reuse) who is not already represented by another role, e.g. manager |
| Provider Service Provider | isManagedBy | provider of vocab service, data service, repository as a service |

### Data alignment processes, policies and contracts

From ‘my data’ to Our FAIR data

It is proposed that ANSIS uses the FAIR Data Policy and ANSIS Trusted Repository Policy as non-binding, guiding principles to define the qualifying levels required for data to be provided as ANSIS Data.

Individual providers’ heterogeneous data and provisioning arrangements can be brought into alignment with agreed ANSIS levels of FAIRness and repository trustedness.

ANSIS FAIR Data policy is based on FAIR principles

It is proposed that ANSIS have a FAIR Data Self-assessment based on the ARDC FAIR Data Self-assessment Tool but incorporates maturity models to measure and track increases in interoperability delivered through services.

The development of the Assessment is explained further in the Appendix 3.

It is proposed that the ANSIS Trusted Repository Policy be based on CoreTrustSeal Data Repositories Requirements.

The development of the Assessment is explained further in the Appendix 4.

### Technical: ANSIS FAIR Data Policy

Proposed ANSIS FAIR Data Policy

- ANSIS FAIR Data Self-assessment will be developed to be used as the data alignment process for ANSIS.

- The FAIR Data Self-assessment will define acceptable levels of FAIRness (Finable, Accessible, Interoperable, Resuable) for data for ANSIS (Table 2).

- Standards for data provision including vocabulary standards will be defined as part of the ANSIS FAIR Data Policy settings.

- Additional data structure semantics and syntax standards may be specified as part of the ANSIS FAIR Data Policy.

- The ANSIS Data Steward will review and approve (or reject) Data Provider Communities’ ANSIS FAIR Data Self-assessments.

- Any disputes in relation to the validation of assessment will be escalated to the Technical Group for review.

- The FAIR assessment process and settings (including qualifying threshold levels) may be modified by the Project Committee on recommendation from the Technical Group.

Table 2: ANSIS FAIR Data Self-assessment proposed initial settings.

### Technical: ANSIS Trusted Repository Policy

Proposed ANSIS Trusted Repository Policy

- It is proposed that the ANSIS Trusted Repository Self-assessment process be developed for use in the ANSIS alignment process.

- Assessment (scope and requirements) may be modified by the ANSIS Project Committee.

- Current thresholds for qualification are proposed as shown in the table on this page. If R2, R3, R4, R11 and R13 to R16 requirements are met, the repository qualifies as an ANSIS Trusted Repository.

- An additional requirement that repository metadata must be harvestable by Research Data Australia (RDA).

- The ANSIS Data Steward will review and qualify (or reject) Data Provider Communities’ ANSIS Trusted Repository Self-assessment.

- Any disputes in relation to the validation of assessment will be escalated to the Technical Group for review.

- Qualifying threshold levels can be modified by the Project Committee on recommendation from the Technical Group.

Table 3: Proposed ANSIS Trusted Repository Self-assessment process.

|  | Requirement | ANSIS policy |
| --- | --- | --- |
| R1 | Mission/Scope: The repository has an explicit mission to provide access to and preserve data in its domain. |  |
| R2 | Licenses: The repository maintains all applicable licenses covering data access and use and monitors compliance. | Yes |
| R3 | Continuity of Access: The repository has a continuity plan to ensure ongoing access to and preservation of its holdings. | Yes |
| R4 | Confidentiality/Ethics: The repository ensures, to the extent possible, that data are created, curated, accessed, and used in compliance with disciplinary and ethical norms. | Yes |
| R5 | Organisational Infrastructure: The repository has adequate funding and sufficient numbers of qualified staff managed through a clear system of governance to effectively carry out the mission. |  |
| R6 | Expert Guidance: The repository adopts mechanism(s) to secure ongoing expert guidance and feedback (either in- house, or external, including scientific guidance, if relevant). |  |
| R7 | Digital Object Management: The repository guarantees the integrity and authenticity of the data. |  |
| R8 | Appraisal: The repository accepts data and metadata based on defined criteria to ensure relevance and understand ability for data users. |  |
| R9 | Documented Storage Procedures: The repository applies documented processes and procedures in managing archival storage of the data. |  |
| R10 | Preservation Plan: The repository assumes responsibility for long-term preservation and manages this function in a planned and documented way. |  |
| R11 | Data Quality: The repository has appropriate expertise to address technical data and metadata quality and ensures that sufficient information is available for end users to make quality-related evaluations. | Yes |
| R12 | Workflows: Archiving takes place according to defined workflows from ingest to dissemination. |  |
| R13 | Data Discovery and Identification: The repository enables users to discover the data and refer to them in a persistent way through proper citation. | Yes |
| R14 | Data Reuse: The repository enables reuse of the data over time, ensuring that appropriate metadata are available to support the understanding and use of the data. | Yes |
| R15 | Technical infrastructure: The repository functions on well-supported operating systems and other core infrastructural software and is using hardware and software technologies appropriate to the services it provides to its users. | Yes |
| R16 | Security: The technical infrastructure of the repository provides for protection of the facility and its data, products, services, and users. | Yes |

## Information Viewpoint

The Information Viewpoint defines the scope of data, and specifies standards used to achieve interoperability.

Principles

The ANSIS data integration and interoperability principles are:

- The Data Provider’s repository should be trustworthy.

- The Data Provider follows the FAIR principles (i.e. the data should be as “FAIR” as possible).

- The dataset interoperability should be mature.

### Data interoperability maturity

Where possible, it is proposed that data should be made interoperable through the adoption of agreed ontologies and vocabulary services (semantic interoperability), agreed data structures (schematic interoperability), and standard communication protocols (syntactic interoperability), along with the adoption of appropriate social architecture for maintaining cross-domain interoperability.

From a technical perspective, levels of interoperability (Brodaric and Gahegan, 2006) are:

- semantic interoperability: harmonised concepts and content.

- schematic interoperability: agreed data structures achieved through the use of common information exchange models that define appropriate data types and structure.

- syntactic interoperability achieved through the use of common file formats and exchange languages, and spatial representations or patterns for using the standard formats for geographic data.

- system or technical interoperability achieved through the use of standard communication protocols and standard delivery mechanisms.

Figure 6: Database systems interoperability levels (Brodaric and Gahegan, 2006)

### ANSIS data interoperability implementation

#### Vocabularies (semantics)

It is proposed that ANSIS data use published vocabularies endorsed by ANSIS Governance to describe concepts within the data.

## Computational Viewpoint

The Computational Viewpoint focuses on the distribution of a system through functional decomposition into objects that interact at interfaces.

### ANSIS Computational Viewpoint Stack

Figure 7: Diagram of a high-level view of the interactions between provider and users via provider and common computational components.

## Engineering Viewpoint

The Engineering Viewpoint focuses on the mechanisms and functions required to support distributed interaction among objects in the system.

### Distributed data supply chain patterns

It is proposed that the preference for ANSIS is to use a federated approach to data supply.

However, where it makes integration easier to achieve, elements of the centralised, brokering and aggregation patterns may also be used.

- For federated and brokered data, source data resides with the Data Provider system. Both solutions encourage currency and validity of data.

- Centralised data will be maintained on CSIRO systems.

- A standards based Service Oriented Architecture is utilised, including metadata cataloguing and vocabulary linking. These will provide information about the data using standardised terms.

- Data is transformed from services developed using a community application schema, or in the case of aggregation, using a respected standards based aggregation platform which has broad appeal.

Figure 8: Distributed data supply chain patterns (Box et al., 2015).

### ANSIS Engineering viewpoint

Figure 9: Diagram of a high-level view of the Engineering viewpoint.

## Technology Viewpoint

The Technology Viewpoint focuses on the choice of technology for a system.

### ANSIS Technology viewpoint – Feature instance

Figure 10: Diagram of a (spatial) ‘feature oriented’ view of the technology stack which emphasises the delivery of geospatial feature data.

# Governance of ANSIS post Project

Sections 1 and 2 proposed a governance framework for ANSIS (the System) for the duration of the Project (2021-2023). During the Project, a post-Project governance framework will be developed and proposed, including a transition plan from Project governance to post-Project collaborative governance if this is the preferred option.

A potential governance model for ANSIS post-Project could be based on the AgReFed Governance Framework (Box et al., 2019; Wong et al., 2021).

Key aspects of AgReFed’s social architecture are listed below.

- AgReFed is a Federation, comprised of autonomous Data Provider Communities.

- AgReFed is governed by a Federation Council and Technical Committee, whose membership is made up of representatives of the Data Provider Communities.

  - The Federation Council is the strategic and business decision making body, responsible for the overall direction, management and (business) operation of the AgReFed.

  - The Federation Technical Committee is the technical decision making body, responsible for decisions about common technology choices, data standards and acceptable qualifying levels. The technical body would report and be accountable to the Federation Council.

- Policies are produced by the Federation Council and Technical Committee, to guide both Data Providers and the Federation.

- Roles performed by community members to govern and operate AgReFed.

- Processes is in place to ensure long term availability of FAIR agricultural data through AgReFed.

The suitability of the AgReFed model for ANSIS requires further consideration.

# References

Box, P. et al. (2015) A Data Specifications Framework for the Foundation Spatial Data Framework.

Box, P. et al. (2019) Guidelines for the development of a Governance Framework for the Agricultural Research Federation (AgReFed). Available at: https://www.researchgate.net/publication/333732404.

Brodaric, B. and Gahegan, M. (2006) ‘Representing geoscientific knowledge in cyberinfrastructure: Some challenges, approaches, and implementations’, Special Paper of the Geological Society of America, 397, pp. 1–20. doi: 10.1130/2006.2397(01).

FAIR Principles - GO FAIR (no date). Available at: https://www.go-fair.org/fair-principles/ (Accessed: 7 June 2022).

Mons, B. et al. (2017) ‘Cloudy, increasingly FAIR; Revisiting the FAIR Data guiding principles for the European Open Science Cloud’, Information Services and Use, 37(1), pp. 49–56. doi: 10.3233/ISU-170824.

Wilkinson, M. D. et al. (2016) ‘The FAIR Guiding Principles for scientific data management and stewardship’, Scientific Data 2016 3:1, 3(1), pp. 1–9. doi: 10.1038/sdata.2016.18.

Wong, M. et al. (2021) Agricultural Research Federation ( AgReFed ) Steering Policies , Roles and Responsibilities.

# Appendix

Minimum metadata elements for collection records

Proposed minimum metadata requirements for ANSIS Collection Descriptions in Research Data Australia, to meet ANSIS FAIR Data Policy.

Fields based on RIF-CS schema (as used by Research Data Australia).

See Australian Research Data Commons for more information on each field.

| Information type (field) | Meaning |
| --- | --- |
| Metadata publisher | The organisation that is contributing the metadata record |
| Identifier | A unique identifier for the resource, i.e. DOI |
| Metadata source | The primary/authoritative source of truth for the metadata record, as represented by a URI. |
| Collection Type | The type of collection being described, i.e. collection, dataset, software, etc |
| Title | The name or title of the collection, should be descriptive and unique, avoid acronyms. |
| Parties | A related person or organisation linked to the collection (include ORCID if possible) e.g. creator, owner, manager. |
| Location | Online location (DOI, Handle or URL) of the metadata record OR to download the resource |
| Related Service | Include a link to the ANSIS portal Research Data Australia record; or to other Services. |
| Citation | The preferred form for citing a collection to enable data to be referenced. |
| Access Rights | Collection access conditions. Specify one of: open, conditional or restricted. |
| Licence | License conditions associated with the collection; a standard licence, e.g. creative commons is preferred. |
| Description | A summary description of the collection. Provide sufficient information to enable a user to assess suitability of the data for reuse for their purpose. |
| Subject | Keywords or terms to describe the topic of the resource. |
| Spatial coverage (if relevant) | The geometry for the location the resource relates to. |
| Temporal coverage (if relevant) | The time period the resource relates to, in W3C Date/Time Format. |

Minimum metadata elements for service records

Proposed minimum metadata requirements for ANSIS Collection Descriptions in Research Data Australia, to meet ANSIS FAIR Data Policy.

Fields based on RIF-CS schema (as used by Research Data Australia).

See Australian Research Data Commons for more information on each field.

| Information type (field) | Meaning |
| --- | --- |
| Metadata publisher | The organisation that is contributing the metadata record |
| Identifier | A unique identifier for the resource, i.e. DOI |
| Metadata source | The primary/authoritative source of truth for the metadata record, as represented by a URI. |
| Service Type | The type of service being described, from this list. |
| Service name | The name or title of the service, should be descriptive and unique, avoid acronyms. |
| Parties related to this service | A related person or organisation linked to the service (include ORCID if possible) e.g. owner, manager. |
| Service location | An electronic address (e.g. access URL) where the service may be accessed. |
| Related Collections | All collections that are related to, or may be accessed by, the ANSIS portal. |
| Access Rights | Service access conditions. Specify one of: open, conditional or restricted. |
| Description | A summary description of the collection. Provide sufficient information to enable a user to assess suitability of the data for reuse for their purpose. |
| Subject | Keywords or terms to describe the research focus of the service. |
| Spatial coverage* | The geometry for the location the resource relates to (a point or a polygon). |
| Temporal coverage* | The time period the resource relates to, in W3C Date/Time Format. |
| Related information* | Related resources such as publications (via DOIs), websites (via URLs), funding info, etc |

ANSIS FAIR Data – alignment process and policy settings

Overview

The FAIR principles (FAIR Principles - GO FAIR, no date; Wilkinson et al., 2016) are a set of guiding principles for rendering data and services Findable, Accessible, and Interoperable, with the ultimate goal of ensuring that research objects are Reusable (Mons et al., 2017). They provide for a continuum of increasing Reusability or ‘FAIRness’, rather than a prescriptive standard which can be failed.

The principles reference community standards and best-practices, rather than defining a specific implementation. It should also be noted that FAIR does not necessarily equal ‘Open’ nor free (i.e. no cost), as there are legitimate reasons why not all data should be openly shared; rather ‘FAIRness’ requires clear and transparent conditions for access and reuse, including a data licence.

Data providers can use the ANSIS FAIR Data Self-Assessment to assess data products, and inform how each component of findability, accessibility, interoperability and reusability can be improved incrementally.

ANSIS FAIR Data Policy

Policies set by ANSIS will be used to determine the acceptable level of FAIRness (e.g. requisite level of metadata and data content standardisation) that will be need to be met for sharing of that data through the ANSIS. These levels may vary between datatypes and may change over time.

The completed ANSIS FAIR Data Self-Assessments will be reviewed and validated by ANSIS Data Stewards against the agreed ANSIS FAIRData Policy.

ANSIS Trusted Repositories - alignment processes and policies

Overview

In a distributed information system such as the ANSIS, the Data Providers’ repositories need to be reliable and trustworthy. The CoreTrustSeal certification provides a process whereby custodians can measure repository compliance levels against sixteen identified characteristics of trustworthy repositories, the Core Trustworthy Data Repositories Requirements (hereafter referred to as the CoreTrustSeal requirements):

R1. Mission/Scope

R2. Licenses

R3. Continuity of Access

R4. Confidentiality/Ethics

R5. Organisational Infrastructure

R6. Expert Guidance

R7. Digital Object Management

R8. Appraisal

R9. Documented Storage Procedures

R10. Preservation Plan

R11. Data Quality

R12. Workflows

R13. Data Discovery and Identification

R14. Data Reuse

R15. Technical infrastructure

R16. Security

How are the CoreTrustSeal requirements being applied in ANSIS?

As with the ANSIS FAIR Data Self-assessment, providers wishing to share data via the ANSIS will conduct an assessment of the repository through which the data will be made persistently available (ANSIS Trusted Repository Self- assessment).

The ANSIS uses a simplified process based on the CoreTrustSeal requirements, but instead of five levels of compliance for each of the requirements, ANSIS assesses whether each requirement has been implemented or not.

The Data Provider Communities will undertake ANSIS Trusted Repository Self- assessments of their repositories. The ANSIS Data Steward (or other agreed community role) will review and validate the assessment against the agreed ANSIS Trusted Repository Policy.

ANSIS Trusted Repository Policy

The ANSIS Trusted Repository Policy set by ANSIS will be used to determine the acceptable level of trustworthiness that will be need to be met for sharing of data through the ANSIS.

Initially it is proposed that for ANSIS the repository meet requirements relating to Licences (R2), Continuity of Access (R3), Confidentiality/Ethics (R4), Data Quality (R11), Data Discovery and Identification (R13), Data Reuse (R14), Technical Infrastructure (R15), and Security (R16). These requirements may change over time.

As Australia’s national science agency and innovation catalyst, CSIRO is solving the greatest challenges through innovative science and technology. CSIRO. Unlocking a better future for everyone. Contact us 1300 363 400 +61 3 9545 2176 csiro.au/contact csiro.au

For further information Agriculture and Food Peter Wilson +61 (0)2 6246 5860 peter.wilson@csiro.au csiro.au Agriculture and Food Jeda Palmer +61 (0)7 3214 2414 jeda.palmer@csiro.au csiro.au